## CR-05 - Goals and Outcomes

**Progress the jurisdiction has made in carrying out its strategic plan and its action plan. 91.520(a)**

This could be an overview that includes major initiatives and highlights that were proposed and executed throughout the program year.

As a brand new entitilement jurisdiction and no experience administrating CDBG or HOME funds under the State Program Marion County faced many obstacles in its first year as an entilement jurisdiction. While the program year began July 1, 2021 Marion County did not recieve approval of its consolidated plan until December 1, 2021. Due to the three declared disaster within the County, staff capacity at the time was limited and therefore delays occured. However, Marion County was able to complete its first Substantial Amendment and realign funds to eligible programs to help move the program forward. As of June 30, 2022 the programs are not up and running, but are close to being operational. Marion County also procured software that it is developing in order to become more efficient in managing all projects in the future. Marion County also completed adopting its policy and procedures that are required as an entitlement jurisdiction including: Section 3 Plan, VAWA, CDBG Policy and Pocedure Manuals, HOME Program Manual, Resale & Recapture Policy, Limited English Proficiency Plan and numerous other plans/policies/manuals. While the bulk of staff time spent in year one was developing these pieces Marion County did add additional staff in March. Marion County anticipates that with this foundation now in place year two will operate more efficiently even as more process and programs are developed.

**Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives. 91.520(g)**

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Goal** | **Category** | **Source / Amount** | **Indicator** | **Unit of Measure** | **Expected – Strategic Plan** | **Actual – Strategic Plan** | **Percent Complete** | **Expected – Program Year** | **Actual – Program Year** | **Percent Complete** |
| Encourage Economic Opportunities | Non-Housing Community Development | CDBG: $ | Businesses assisted | Businesses Assisted | 5 | 0 | 0.00% |  |  |  |
| Increase Access to Community Services | Non-Homeless Special Needs | CDBG: $ | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 16000 | 0 | 0.00% |  |  |  |
| Increase Availability and Affordability of Housing | Affordable Housing | CDBG: $ / HOME: $ | Rental units constructed | Household Housing Unit | 5 | 0 | 0.00% |  |  |  |
| Increase Availability and Affordability of Housing | Affordable Housing | CDBG: $ / HOME: $ | Homeowner Housing Rehabilitated | Household Housing Unit | 100 | 0 | 0.00% | 54 | 0 | 0.00% |
| Increase Availability and Affordability of Housing | Affordable Housing | CDBG: $ / HOME: $ | Direct Financial Assistance to Homebuyers | Households Assisted | 200 | 0 | 0.00% | 19 | 0 | 0.00% |
| Invest in Vital Comm. Facilities & Infrastructure | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 10000 | 0 | 0.00% | 2000 | 0 | 0.00% |
| Provide for CHDO Set-Aside | Affordable Housing | HOME: $ | Other | Other | 5 | 0 | 0.00% | 1 | 0 | 0.00% |
| Support Disaster Recovery Efforts | Affordable Housing Non-Housing Community Development | CDBG: $ / HOME: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 15000 | 0 | 0.00% |  |  |  |
| Support Disaster Recovery Efforts | Affordable Housing Non-Housing Community Development | CDBG: $ / HOME: $ | Rental units constructed | Household Housing Unit | 5 | 0 | 0.00% |  |  |  |
| Support Disaster Recovery Efforts | Affordable Housing Non-Housing Community Development | CDBG: $ / HOME: $ | Homeowner Housing Added | Household Housing Unit | 1 | 0 | 0.00% |  |  |  |
| Support Disaster Recovery Efforts | Affordable Housing Non-Housing Community Development | CDBG: $ / HOME: $ | Homeowner Housing Rehabilitated | Household Housing Unit | 25 | 0 | 0.00% | 6 | 0 | 0.00% |
| Support Program Success | Non-Housing Community Development | CDBG: $ / HOME: $ | Other | Other | 5 | 0 | 0.00% | 1 | 0 | 0.00% |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

**Assess how the jurisdiction’s use of funds, particularly CDBG, addresses the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified.**

The only funds expended in year one was for administration which included paying for the consultant who  developed the Consolidated Plan, Analysis of Impediments, and the 2021 Annual Action Plan. With the substantial amendment completed and funds directed to eligible programs funds remain in alignment with some of the highest priority activities identified in the Consolidated Plan. For example, Direct Financial assistance will be provided to first time homebuyers under the Down Payment Assistance program being established. This fits within the overall goal of increasing availability and affordability of housing options. The County also has realigned funds into the rehabilitation program. The design of the program will benefit household within the disaster recovery area via septic systems/wells and increasing the availability and affordability of housing options. Once these programs begin, funds will be in alignment with the highest priorities of the County. The County did complete a draw for Center for Hope and Safety for Architect and Engineering costs to their new addition. Since the building has not been built there is no outcome to report at this time. The building is set to be completed in spring of 2024 which then the project will officially meet a national objective of LMC benefit.

## CR-10 - Racial and Ethnic composition of families assisted

**Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)**

|  |  |  |
| --- | --- | --- |
|  | **CDBG** | **HOME** |
| White | 0 | 0 |
| Black or African American | 0 | 0 |
| Asian | 0 | 0 |
| American Indian or American Native | 0 | 0 |
| Native Hawaiian or Other Pacific Islander | 0 | 0 |

|  |  |  |
| --- | --- | --- |
|  |  |  |
| **Total** | **0** | **0** |

|  |  |  |
| --- | --- | --- |
|  |  |  |
| Hispanic | 0 | 0 |
| Not Hispanic | 0 | 0 |

**Table 2 – Table of assistance to racial and ethnic populations by source of funds**

**Narrative**

Due to not having any projects/activities accomplished there is no racial and ethnic composition to report.

## CR-15 - Resources and Investments 91.520(a)

**Identify the resources made available**

|  |  |  |  |
| --- | --- | --- | --- |
| **Source of Funds** | **Source** | **Resources Made Available** | **Amount Expended During Program Year** |
| CDBG | public - federal | 1,561,194 |  |
| HOME | public - federal | 621,125 |  |

Table 3 - Resources Made Available

**Narrative**

The only funds that were expended within the 2021 Program Year was administrative funds.

**Identify the geographic distribution and location of investments**

|  |  |  |  |
| --- | --- | --- | --- |
| **Target Area** | **Planned Percentage of Allocation** | **Actual Percentage of Allocation** | **Narrative Description** |
| LMI Areas |  |  | LMI Areas |
| Marion County Service Area | 100 |  | Service Area |

Table 4 – Identify the geographic distribution and location of investments

**Narrative**

The only funds that were expended within the 2021 Program Year was administrative funds which is related to the whole service area.

**Leveraging**

**Explain how federal funds leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.**

There were not funds leveraged as part of the 2021 Program Year.

| **Fiscal Year Summary – HOME Match** | |
| --- | --- |
| 1. Excess match from prior Federal fiscal year | 0 |
| 2. Match contributed during current Federal fiscal year | 0 |
| 3. Total match available for current Federal fiscal year (Line 1 plus Line 2) | 0 |
| 4. Match liability for current Federal fiscal year | 0 |
| 5. Excess match carried over to next Federal fiscal year (Line 3 minus Line 4) | 0 |

Table 5 – Fiscal Year Summary - HOME Match Report

| **Match Contribution for the Federal Fiscal Year** | | | | | | | | |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Project No. or Other ID** | **Date of Contribution** | **Cash**  **(non-Federal sources)** | **Foregone Taxes, Fees, Charges** | **Appraised Land/Real Property** | **Required Infrastructure** | **Site Preparation, Construction Materials, Donated labor** | **Bond Financing** | **Total Match** |
|  |  |  |  |  |  |  |  |  |

Table 6 – Match Contribution for the Federal Fiscal Year

**HOME MBE/WBE report**

| **Program Income** – Enter the program amounts for the reporting period | | | | |
| --- | --- | --- | --- | --- |
| **Balance on hand at begin-ning of reporting period**  **$** | **Amount received during reporting period**  **$** | **Total amount expended during reporting period**  **$** | **Amount expended for TBRA**  **$** | **Balance on hand at end of reporting period**  **$** |
| 0 | 0 | 0 | 0 | 0 |

Table 7 – Program Income

|  |
| --- |
| **Minority Business Enterprises and Women Business Enterprises –** Indicate the number and dollar value of contracts for HOME projects completed during the reporting period |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Total** | **Minority Business Enterprises** | | | | **White Non-Hispanic** |
| **Alaskan Native or American Indian** | **Asian or Pacific Islander** | **Black Non-Hispanic** | **Hispanic** |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Contracts** | | | | | | |
|  |  |  |  |  |  |  |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Sub-Contracts** | | | | | | |
|  |  |  |  |  |  |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Total** | **Women Business Enterprises** | **Male** |

|  |  |  |  |
| --- | --- | --- | --- |
| **Contracts** | | | |
|  |  |  |  |
| Dollar Amount | 0 | 0 | 0 |
| Number | 0 | 0 | 0 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Sub-Contracts** | | | |
|  |  |  |  |
| Number | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 |

Table 8 - Minority Business and Women Business Enterprises

|  |
| --- |
| **Minority Owners of Rental Property** – Indicate the number of HOME assisted rental property owners and the total amount of HOME funds in these rental properties assisted |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Total** | **Minority Property Owners** | | | | **White Non-Hispanic** |
| **Alaskan Native or American Indian** | **Asian or Pacific Islander** | **Black Non-Hispanic** | **Hispanic** |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

Table 9 – Minority Owners of Rental Property

|  |
| --- |
| **Relocation and Real Property Acquisition –** Indicate the number of persons displaced, the cost of relocation payments, the number of parcels acquired, and the cost of acquisition |

|  |  |  |
| --- | --- | --- |
|  | **Number** | **Cost** |
| Parcels Acquired | 0 | 0 |
| Businesses Displaced | 0 | 0 |
| Nonprofit Organizations Displaced | 0 | 0 |
| Households Temporarily Relocated, not Displaced | 0 | 0 |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Households Displaced** | **Total** | **Minority Property Enterprises** | | | | **White Non-Hispanic** |
| **Alaskan Native or American Indian** | **Asian or Pacific Islander** | **Black Non-Hispanic** | **Hispanic** |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Cost | 0 | 0 | 0 | 0 | 0 | 0 |

Table 10 – Relocation and Real Property Acquisition

## CR-20 - Affordable Housing 91.520(b)

**Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.**

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of Homeless households to be provided affordable housing units | 0 | 0 |
| Number of Non-Homeless households to be provided affordable housing units | 55 | 0 |
| Number of Special-Needs households to be provided affordable housing units | 0 | 0 |
| **Total** | **55** | **0** |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through Rental Assistance | 0 | 0 |
| Number of households supported through The Production of New Units | 1 | 0 |
| Number of households supported through Rehab of Existing Units | 54 | 0 |
| Number of households supported through Acquisition of Existing Units | 0 | 0 |
| **Total** | **55** | **0** |

Table 12 – Number of Households Supported

**Discuss the difference between goals and outcomes and problems encountered in meeting these goals.**

Marion County has not accomplished any goals within the first year. However, it anticpates that with the substantial amendment being completed and the foundation established many of the goals stated within year one with the substantial amendment will be accomplished within the 2022 Program Year.

**Discuss how these outcomes will impact future annual action plans.**

All future annual action will include projects that will be completed within a timly manner as the County will developed the procedures and continues to develop the processes to run an effective and efficient program.

**Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.**

|  |  |  |  |
| --- | --- | --- | --- |
| **Number of Households Served** | **CDBG Actual** | **HOME Actual** | |
| Extremely Low-income | 0 | 0 |
| Low-income | 0 | 0 |
| Moderate-income | 0 | 0 |
| **Total** | **0** | **0** |

Table 13 – Number of Households Served

**Narrative Information**

No funds were dispersed for projects within the 2021 Program Year.

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

**Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:**

**Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs**

Marion County actively participates in the Continuum of Care and is looking for ways to help reduce homelessness as it was a priority identified in the Consolidated Plan. Marion County also provided funding to the City of Silverton through its ARPA allocation to help purchase a modular building to serve as a resource center to assist unhoused individuals in the community while they work towards permanent housing. Marion County also allocated funding under its 2021 action plan for food bank support for Neighbors Serving Unsheltered Neighbors in Woodburn. Although the project has not moved forward at this time it is anticipated that some amount of funds will be spent toward the project.

**Addressing the emergency shelter and transitional housing needs of homeless persons**

Marion County is helping to expand transitional housing in year 2 of its consolidated plan. Marion County is analyzing ways in which it can continue to address emergency shelter and transitional housing needs.

**Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are: likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions); and, receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs**

There are a number of programs to assit low-income individuals and families to avoid homelessness, including improving rapid re-housing assistance to unsheltered persons, allocating funds to keep people in their homes in time of financial crisis, food assistance and case management is avaialble to help persons and families recover and avoid returing to being unsheltered. Marion County annually funds the Continuum of Care with their homelessness efforts. Marion County continues to make efforts in helping with Wildfire surviviors through the rebuilding process and is aware of the challenges within the wildfire affected areas in regards to homelessness. Marion County continues to actively pursue avenues to help surviviors through its tiny homes projects.

**Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again**

Marion County is having continuous conversations on how to help homeless persons transition to permanent housing and independent living. Marion County is aware of the infrastructure challenges within its jurisdictional boundaries and the timeframe it takes for projects to develop.

## CR-30 - Public Housing 91.220(h); 91.320(j)

**Actions taken to address the needs of public housing**

Marion County staff works closely with the public housing authority on potential projects. It will continue to grow its collaboration in years to come as the CDBG/HOME Program can be a financial partner to future public housing projects if so desired.

**Actions taken to encourage public housing residents to become more involved in management and participate in homeownership**

Marion County is activly pursuing ways for public housing residents to become homeowners. The County is aware of the challenges due to land prices and the ability to purchase property and the financial constraints pertaining to public housing residents. Through a partnership with DevNW Marion County Housing Authority utilizes IDAs for families seeking homeownership. The Public Housing Authority attempts to engage residents via the advisory board, email, and direct mail.

**Actions taken to provide assistance to troubled PHAs**

Marion County Public Housing Authority is not considered a troubled Public Housing Authority.

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

**Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i)**

Marin County is actively pursing ways to help cities meet the growth challenges in Oregon. Marion County is analyzing ways to help alleviate affordable housing barriers but as an Urban County with no jurisdiction within any of its partnering cities many change, if need be, would reside with the individual cities. However, Marion County is also analyzing ways to purchase land to help ease the cost to build housing in general.

**Actions taken to address obstacles to meeting underserved needs. 91.220(k); 91.320(j)**

Marion County is in numerous conversations on how to help address obstacles for underserved communities, including providing technical assistance whenever possible. Marion County is providing funding for the new HOPE Plaza project which will consist of an expansion of the Center for Hope and Safety (Domestic Violence provider) to included retail space and 20 apartments in conjunction with the Salem Housing Authority.

**Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)**

Marion County is committed to reducing any lead-based paint hazards when situations arise. At this time there were no projects that warranted lead-based paint concerns. However, as the programs mature over time Marion County aticipates through rehabilitation, an activity that will begin soon, there may be a need to address lead-based paint hazards in the future.

**Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)**

Marion County reconizes the importance of upward mobility for families of poverty levels. It is important to the County to help families growth wealth by homeownership and therefore funds were allocated for Down Payment Assistance under the 2021 program year. The program itself has just opened and the marketing efforts are underway in order to reach potential homebuyers. Marion County hopes that the program design will be able to help families reach homeownership however, it recognizes there may need to be changes in the amount of assistance as the program accelerates. There is hope that the amount of funding will be able to be matched through state funding or other funds to reach the required amount for potential homebuyers to acquire properties.

**Actions taken to develop institutional structure. 91.220(k); 91.320(j)**

Marion County continues to develop insitutional structure through informational meetings, work sessions, and direct communication with its cities. The Community Development Division is currently in the process of merging with the County's Community Services department which houses the Economic Development team and various other community based projects such as broadband. The County believes this strategic realignment will enable the County to serve the community more efficiently and productively. The County is still working on developing more efficient ways to collaborate with key stakeholders throughout the community and it recently developed a quarterly meeting with the City of Salem to discuss coordination and implementation on current or future projects.

**Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)**

Over the course of the 2021 Program Year Marion County has been in contact with its housing authority on potential projects and how to grow homeownership within the housing authority programs. Marion County Housing Authority will start offering vouchers for homeownership but the program will not be operational for a couple of years. Marion County is currently working on developing a site in Mill City that will include a diverse type of housing. It is anticipated to have approximately 60 homesites with a mix of single family, duplexes and potentially townhomes. Adjacent to this property is where approximately 60 apartments are going to be built. Marion County housing authority also owns a lot adjacent that will include housing. Due to the challenges of the infrastructure in Mill City it is anticipated that construction will begin within the next 5 years. Marion County is allocating funding for transitional housing through ARPA funding and CDBG funding. Marion County continues to look at ways to help bridge the gap in cooridnation with public and private housing and social service agencies.

**Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice. 91.520(a)**

It is the intent of Marion County to develop its fair housing program over the next cycle to really attempt to address some of the impediments identified. There were four key fair housing goals identified in the analysis of impediments. Those four goals were to promote affordable homeownership and rental opportunities, promote community development acitivities in areas with higher rates of poverty, promote community and service provider knowledge of ADA laws, and increase outreach and education for housing providers in the County and the public. As the County continues to develop its CDBG/HOME Program it anticipates fair housing will play an important component  through the process of implementing projects. There are long-term projects through disaster recovery that will be encouraging affordable homeownership and retail opportunities although they are some years away.

## CR-40 - Monitoring 91.220 and 91.230

**Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements**

As Marion County continues to develop its program it is anticipated that monitoring of its subrecipients and all projects will be evolving. This will depend on the type of project due to the different layers of federal requirements. For instance Center for Hope and Safety is strictly on a reimbursement cycle and all rehabs and down payment assistance will be provided as projects are finished or homeowners are about to acquire a home. Since the County is taking on the role of administering these projects keeping track of financial deadlines will be key. All of the project documentation for down payment assistance and rehailitation will be located in Neighborly software so there will be limited need to visit properties as desk audits will be conducted routinly to make sure all project files in Neighborly have the correct documentation uploaded. Otherwise, monitiring for future projects will be on a case-by-case basis in terms of the level of monitoring.

**Citizen Participation Plan 91.105(d); 91.115(d)**

**Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports**.

Marion County currently requires a 30-day public comment period and the County also translates all notices from English and Spanish. The County has developed a comprehensive contact list for Notice of Funding Opportunities, Applications, Annual Action Plans and Consolidated Performance Evaluation Reports. In the future Marion County will be conducting application training and public hearings for application presentations, and allocation of funding. The public hearing notices are identified either in the Stateman Journal or the Woodburn Independent. All public hearings are during the day on Wednesday as the regularlly scheduled board sessions. In the future the County may hold public hearings offsite to be able hear from the public whom may not be able to attend a Wednesday meeting during the day. The draft CAPER/Annual Action Plan and other documents are posted on the County website.

**CR-45 - CDBG 91.520(c)**

**Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.**

There were not changes to the jurisdictions program objectives for CDBG in year one. The Annual Action Plan did require a substantial amendment due to inexperience and timing of the County in administering CDBG. To hopefully combat this issue the County has a plan to start taking preliminary application/inquiries from January through July each year and then working with each individual applicant that moves forward on meeting programmatic requirements and other federal requirements such as procurement that way all projects will be able to be identified in the following years Annual Action Plan well in advance and the applicants will know what is expected.

**Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?**

No

**[BEDI grantees] Describe accomplishments and program outcomes during the last year.**

## CR-50 - HOME 91.520(d)

**Include the results of on-site inspections of affordable rental housing assisted under the program to determine compliance with housing codes and other applicable regulations**

Please list those projects that should have been inspected on-site this program year based upon the schedule in §92.504(d). Indicate which of these were inspected and a summary of issues that were detected during the inspection. For those that were not inspected, please indicate the reason and how you will remedy the situation.

There were no projects that required on-site inspections for affordable rental housing as it is not in the Consolidated Plan and this is the first year the County has been an Entitlement Jurisdiction.

**Provide an assessment of the jurisdiction's affirmative marketing actions for HOME units. 92.351(b)**

Currently, Marion County has no units to market but in the future it will follow all affirmative marketing requirements.

**Refer to IDIS reports to describe the amount and use of program income for projects, including the number of projects and owner and tenant characteristics**

Marion County does not have any program income at this time that will contribute to projects.

**Describe other actions taken to foster and maintain affordable housing. 91.220(k) (STATES ONLY: Including the coordination of LIHTC with the development of affordable housing). 91.320(j)**

Marion County is working on a couple of different affordable housing projects in Mill City that it hopes will be operational by 2025. While not involved there is also an affordable housing complex being developed in Stayton that includes state LIFT funding.

## CR-58 – Section 3

**Identify the number of individuals assisted and the types of assistance provided**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Total Labor Hours** | **CDBG** | **HOME** | **ESG** | **HOPWA** | **HTF** |
| Total Number of Activities | 0 | 0 | 0 | 0 | 0 |
| Total Labor Hours | 0 | 0 |  |  |  |
| Total Section 3 Worker Hours | 0 | 0 |  |  |  |
| Total Targeted Section 3 Worker Hours | 0 | 0 |  |  |  |

Table 15 – Total Labor Hours

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Qualitative Efforts - Number of Activities by Program** | **CDBG** | **HOME** | **ESG** | **HOPWA** | **HTF** |
| Outreach efforts to generate job applicants who are Public Housing Targeted Workers |  |  |  |  |  |
| Outreach efforts to generate job applicants who are Other Funding Targeted Workers. |  |  |  |  |  |
| Direct, on-the job training (including apprenticeships). |  |  |  |  |  |
| Indirect training such as arranging for, contracting for, or paying tuition for, off-site training. |  |  |  |  |  |
| Technical assistance to help Section 3 workers compete for jobs (e.g., resume assistance, coaching). |  |  |  |  |  |
| Outreach efforts to identify and secure bids from Section 3 business concerns. |  |  |  |  |  |
| Technical assistance to help Section 3 business concerns understand and bid on contracts. |  |  |  |  |  |
| Division of contracts into smaller jobs to facilitate participation by Section 3 business concerns. |  |  |  |  |  |
| Provided or connected residents with assistance in seeking employment including: drafting resumes,preparing for interviews, finding job opportunities, connecting residents to job placement services. |  |  |  |  |  |
| Held one or more job fairs. |  |  |  |  |  |
| Provided or connected residents with supportive services that can provide direct services or referrals. |  |  |  |  |  |
| Provided or connected residents with supportive services that provide one or more of the following: work readiness health screenings, interview clothing, uniforms, test fees, transportation. |  |  |  |  |  |
| Assisted residents with finding child care. |  |  |  |  |  |
| Assisted residents to apply for, or attend community college or a four year educational institution. |  |  |  |  |  |
| Assisted residents to apply for, or attend vocational/technical training. |  |  |  |  |  |
| Assisted residents to obtain financial literacy training and/or coaching. |  |  |  |  |  |
| Bonding assistance, guaranties, or other efforts to support viable bids from Section 3 business concerns. |  |  |  |  |  |
| Provided or connected residents with training on computer use or online technologies. |  |  |  |  |  |
| Promoting the use of a business registry designed to create opportunities for disadvantaged and small businesses. |  |  |  |  |  |
| Outreach, engagement, or referrals with the state one-stop system, as designed in Section 121(e)(2) of the Workforce Innovation and Opportunity Act. |  |  |  |  |  |
| Other. |  |  |  |  |  |

Table 16 – Qualitative Efforts - Number of Activities by Program

**Narrative**

Marion County did not fund any projects that require section 3 reporting in 2021.