## Sheet3
Projected Schedule
Chip Seal Treatment | Fog Seal Treatment | Road Name | ​Begin Location | ​End Location | Chip Seal Treatment (week of) | Shot Order (per date) | Shot Order
2025-07-07 | 2025-07-17 | Bean Alley Rd SE | W Stayton Rd | End of Pavement | 2025-07-07 | 1 | 1
2025-07-07 | 2025-07-17 | Snoddy Dr SE | Bean Alley Rd | W Stayton Rd | 2025-07-07 | 2 | 2
2025-07-07 | 2025-07-17 | Jefferson-Marion Rd SE | Parish Gap Rd | Cemetery Hill Rd | 2025-07-07 | 3 | 3
2025-07-08 | 2025-07-17 | Jefferson-Marion Rd SE | Parish Gap Rd | Cemetery Hill Rd | 2025-07-07 | 1 | 4
2025-07-08 | 2025-07-17 | Salamander Rd SE | Dead End (N of Wied Rd) | 1229' N of Cemetery Hill Rd | 2025-07-07 | 2 | 5
2025-07-08 | 2025-07-17 | Cemetery Hill Rd SE | Jefferson-Marion Rd | End of Pavement | 2025-07-07 | 3 | 6
2025-07-09 | 2025-07-17 | Salamander Rd SE | Dead End (N of Wied Rd) | 1229' N of Cemetery Hill Rd | 2025-07-07 | 1 | 7
2025-07-09 | 2025-07-17 | Jefferson-Marion Rd SE | Parish Gap Rd | Cemetery Hill Rd | 2025-07-07 | 2 | 8
2025-07-10 | 2025-07-30 | Talbot Rd S | St Hwy 164 | Miller Rd SE | 2025-07-07 | 1 | 9
2025-07-10 | 2025-07-30 | Talbot Rd S | Miller Rd SE | I-5 R/W (E Side) | 2025-07-07 | 2 | 10
2025-07-14 | 2025-07-30 | Talbot Rd S | Miller Rd SE | I-5 R/W (E Side) | 2025-07-14 | 1 | 11
2025-07-14 | 2025-08-14 | Wintel Rd S | Jorgensen Rd S | Marlatt Rd S | 2025-07-14 | 2 | 12
2025-07-15 | 2025-08-14 | Wintel Rd S | Jorgensen Rd S | Marlatt Rd S | 2025-07-14 | 1 | 13
2025-07-15 | 2025-08-14 | Wintel Rd S | Marlatt Rd S | Buena Vista Rd S | 2025-07-14 | 2 | 14
2025-07-15 | 2025-08-13 | Marlatt Rd S | Wintel Rd | Talbot Rd | 2025-07-14 | 3 | 15
2025-07-16 | 2025-08-13 | Marlatt Rd S | Wintel Rd | Talbot Rd | 2025-07-14 | 1 | 16
2025-07-16 | 2025-08-13 | Marlatt Rd S | Talbot Rd S | 256' S. of Talbot | 2025-07-14 | 2 | 17
2025-07-16 | 2025-08-13 | Ankeny Hill Rd SE | I-5 Off Ramp | 3906' west of Wintel Rd S | 2025-07-14 | 3 | 18
2025-07-16 | 2025-08-13 | Ankeny Hill Rd SE | 3906' west of Wintel Rd S | Liberty Rd | 2025-07-14 | 4 | 19
2025-07-21 | 2025-08-13 | Wintel Rd S | Ankeny Hill Rd | Jorgensen Rd | 2025-07-21 | 1 | 20
2025-07-21 | 2025-08-14 | Jorgenson Rd S | Wintel Rd | Talbot Rd S | 2025-07-21 | 2 | 21
2025-07-21 | 2025-07-31 | Talbot Rd S | I-5 R/W (Westside Ln) | Marlett Rd | 2025-07-21 | 3 | 22
2025-07-22 | 2025-08-14 | Talbot Rd S | I-5 R/W (Eastside Lane) | Marllat Rd S | 2025-07-21 | 1 | 23
2025-07-22 | 2025-08-14 | Talbot Rd S | Marlatt Rd S | Gilmore Rd S | 2025-07-21 | 2 | 24
2025-07-22 | 2025-08-14 | Talbot Rd S | Gilmore Rd S | Buena Vista Rd S | 2025-07-21 | 3 | 25
2025-07-22 | TBD | Buena Vista Rd S | Ferry Landing | Gilmore Rd S | 2025-07-21 | 4 | 26
2025-07-23 | TBD | Buena Vista Rd S | Ferry Landing | Gilmore Rd S | 2025-07-21 | 1 | 27
2025-07-23 | TBD | Buena Vista Rd S | Gilmore Rd S | RR Crossing | 2025-07-21 | 2 | 28
2025-07-24 | TBD | Buena Vista Rd S | RR Crossing | Ankeny Hill Dr S | 2025-07-21 | 1 | 29
2025-07-24 | TBD | Oak Dr SE | Ankeny Hill Rd | Lake Dr | 2025-07-21 | 2 | 30
2025-07-24 | TBD | Fir Pl SE | Oak Dr | Cul-De-Sac | 2025-07-21 | 3 | 31
2025-07-28 | TBD | Lake Dr SE | Liberty Rd | Oak Dr | 2025-07-28 | 1 | 32
2025-07-28 | 2025-08-13 | Wintel Rd S | Ankeny Hill Rd | Jorgensen Rd | 2025-07-28 | 2 | 33
2025-07-28 | TBD | Sidney Rd S | Buena Vista Rd | Riverside Rd | 2025-07-28 | 3 | 34
2025-07-29 | TBD | Sidney Rd S | Buena Vista Rd | Riverside Rd | 2025-07-28 | 1 | 35
2025-07-29 | TBD | Riverside Rd S | Sidney Rd | Skyline Dr | 2025-07-28 | 2 | 36
2025-08-04 | TBD | Riverside Rd S | Sidney Rd | Skyline Dr | 2025-08-04 | 1 | 37
2025-08-04 | TBD | Riverside Rd S | Wood Bridge | River Rd S | 2025-08-04 | 2 | 38
2025-08-05 | TBD | Riverside Rd S | Wood Bridge | River Rd S | 2025-08-04 | 1 | 39
2025-08-05 | TBD | Skyline Rd S | Riverside Rd | Comcomly Dr S | 2025-08-04 | 2 | 40
2025-08-05 | TBD | Skyline Rd S | Comcomly Dr S | Cole Rd S | 2025-08-04 | 3 | 41
2025-08-06 | TBD | West Nanitch Cr S | Cul-De-Sac | Saghali Dr | 2025-08-04 | 1 | 42
2025-08-06 | TBD | East Nanitch Cr S | Cul-De-Sac | Saghalie Dr | 2025-08-04 | 2 | 43
2025-08-06 | TBD | Kalakala Cr S | Cul-De-Sac | Saghalie Dr | 2025-08-04 | 3 | 44
2025-08-06 | TBD | Kwonesum Ct S | Cul-De-Sac | Saghalie Dr | 2025-08-04 | 4 | 45
2025-08-06 | TBD | Saghalie Dr S | Concomly Dr (E. Int) | Concomly Dr (W Int) | 2025-08-04 | 5 | 46
2025-08-07 | TBD | Saghalie Dr S | Concomly Dr (E. Int) | Concomly Dr (W Int) | 2025-08-04 | 1 | 47
2025-08-07 | TBD | Tillikam Ct S | Cul-De-Sac | Concomly Rd S | 2025-08-04 | 2 | 48
2025-08-07 | TBD | Kloshe Ct S | Concomly Rd | Cul-De-Sac | 2025-08-04 | 3 | 49
2025-08-07 | TBD | Kaloken Ct S | Konaway Lp | Etomina Ln | 2025-08-04 | 4 | 50
2025-08-07 | TBD | Talis Ct | Cul-De-Sac | Konaway Lp | 2025-08-04 | 5 | 51
2025-08-07 | TBD | Konaway Lp S | Concomly Rd S | 436' E of Otegh Ln | 2025-08-04 | 6 | 52
2025-08-11 | TBD | Konaway Lp S | 436' E of Otegh Ln | Concomly Rd S (W Int) | 2025-08-11 | 1 | 53
2025-08-11 | TBD | Concomly Rd S | Bates Rd S | Kloshe Ct S | 2025-08-11 | 2 | 54
2025-08-11 | TBD | Concomly Rd S | Kloshe Ct S | #3012 Concomly Rd S | 2025-08-11 | 3 | 55
2025-08-11 | TBD | Concomly Rd S | #3012 Concomly Rd S | Skyline Rd S | 2025-08-11 | 4 | 56
2025-08-12 | TBD | Cole Rd S | End of Pavement (E of Moore) | End of Pavement (W of Moore) | 2025-08-11 | 1 | 57
2025-08-12 | TBD | Cole Rd S | End of Pavement | Skyline Rd S | 2025-08-11 | 2 | 58
2025-08-12 | TBD | Skyline Rd S | Cole Rd | Ruggles Ave S | 2025-08-11 | 3 | 59
2025-08-12 | TBD | Skyline Rd S | Ruggles Rd S | Vitae Springs Rd | 2025-08-11 | 4 | 60
2025-08-18 | TBD | Skyline Rd S | Vitae Springs Rd | Salem C/L | 2025-08-18 | 1 | 61
2025-08-18 | TBD | Davis Rd S | 586' E of Skyline Rd | Skyline Rd S | 2025-08-18 | 2 | 62
2025-08-18 | TBD | Newberry St S | Skyline Rd | End of Pavement | 2025-08-18 | 3 | 63
2025-08-18 | TBD | Inwood Ln S | Beg. of Pavement | Vitae Springs Rd | 2025-08-18 | 4 | 64
2025-08-18 | TBD | River Springs Dr S | Prospect Ridge Rd | Vitae Springs Rd | 2025-08-18 | 5 | 65
2025-08-18 | TBD | Orville Rd | River Rd | Vitae Springs Rd | 2025-08-18 | 6 | 66
2025-08-19 | TBD | Orville Rd | River Rd | Vitae Springs Rd | 2025-08-18 | 1 | 67
2025-08-19 | TBD | Vitae Springs Rd S | Orville Rd | House #4352 | 2025-08-18 | 2 | 68
2025-08-19 | TBD | Vitae Springs Rd S | House #4352 | Skyline Rd | 2025-08-18 | 3 | 69
2025-08-20 | TBD | Vitae Springs Rd S | House #4352 | Skyline Rd | 2025-08-18 | 1 | 70
2025-08-20 | TBD | Quinalt St SE | End of Pavement | Liberty Rd | 2025-08-18 | 2 | 71
2025-08-20 | TBD | Hylo Rd SE | Liberty Rd | Sunnyside Rd | 2025-08-18 | 3 | 72